Appendices

List of the Appendices:

- Schedule of Master Thesis	………………………………………………II

- Daily readings of pH, ORP and Biogas Production from the

Sugarcane bagasse and cow manure batch assay……………………..……..III

- Daily readings of pH, ORP and Biogas Production from the

Sugarcane bagasse and cow manure batch assay…………………….……..IV

- Means Plot of the two batch tests…………………………………………..IV

- Taking samples for pH and ORP test……………………………..……….V

- A picture with some of the farmers in the study area………………….…..VI

- A picture with the head of farmers in study area on his Sugarcane farm......VII

Appendix 1: Schedule of Master Thesis

| Activity | Time Frame |
| --- | --- |
| Writing and Approval of Proposal |  |
| Further Literature Review |  |
| Design of Methodology and Approval | 1 week |
| Questionnaire Design and Approval | 2 weeks |
| Data Collection and Collation | August 1st – December 3rd |
| Data entry and Analysis | December 19th – January 30th |
| Interpretation of Results | February 3rd – March 20th |
| Conclusion and Recommendation | April 11th – 18th |
| Review of Thesis | April |
| Final Submission | April |

Appendix 2: Daily readings of pH, ORP and Biogas Production from the Sugarcane bagasse and cow manure batch assay.

| Day | Date / time | ph | ORP [mV] | Gas volume [ml] |
| --- | --- | --- | --- | --- |
| 0 | 3/25/23 17:00 | 7.61 | -339.4 | 0 |
| 2 | 3/27/23 17:00 | 7.09 | -344.1 | 495 |
| 4 | 3/29/23 17:00 | 7.4 | -378.5 | 505 |
| 6 | 3/31/23 17:00 | 7.48 | -381.6 | 1025 |
| 8 | 4/2/23 17:00 | 7.56 | -377.8 | 1335 |
| 10 | 4/4/23 17:00 | 7.79 | -379.8 | 325 |
| 12 | 4/6/23 17:00 | 7.6 | -344.6 | 935 |
| 14 | 4/8/23 17:00 | 7.65 | -325.7 | 600 |
| 16 | 4/10/23 17:00 | 7.74 | -332 | 650 |
| 18 | 4/12/23 17:00 | 7.35 | -341.5 | 255 |
| 20 | 4/14/23 17:00 | 7.32 | -335.6 | 125 |
| 22 | 4/16/23 17:00 | 7.16 | -332.4 | 75 |
| 24 | 4/18/23 17:00 | 6.98 | -328.8 | 35 |

Appendix 3: Daily readings of pH, ORP and Biogas Production from the Sugarcane bagasse batch assay.

| Day | Date / time | Ph | ORP [mV] | Gas volume [ml] |
| --- | --- | --- | --- | --- |
| 0 | 3/25/23 17:00 | 7.61 | -324.8 | 0 |
| 2 | 3/27/23 17:00 | 7.25 | -408.2 | 935 |
| 4 | 3/29/23 17:00 | 7.43 | -364.8 | 765 |
| 6 | 3/31/23 17:00 | 7.56 | -375 | 652 |
| 8 | 4/2/23 17:00 | 7.6 | -412.2 | 870 |
| 10 | 4/4/23 17:00 | 7.59 | -458 | 210 |
| 12 | 4/6/23 17:00 | 7.55 | -360.8 | 1130 |
| 14 | 4/8/23 17:00 | 7.59 | -351.3 | 810 |
| 16 | 4/10/23 17:00 | 7.53 | -351.3 | 550 |
| 18 | 4/12/23 17:00 | 7.44 | -340 | 235 |
| 20 | 4/14/23 17:00 | 7.45 | -332 | 110 |
| 22 | 4/16/23 17:00 | 7.36 | -366.1 | 60 |
| 24 | 4/18/23 17:00 | 7.37 | -353.6 | 25 |

Appendix 4: Means Plot of the two batch tests.

Appendix 5: Taking samples for pH and ORP test.

Appendix 6: A picture with some of the farmers in the study area

Appendix 7: A picture with the head of farmers in study area on his sugarcane farm.